## Catlog
Project Name | FOODBOX
StakeHolders/Customers/Users | foodpanda/abc
Created By | Product Owner
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
For a foodbox restaurant to launch a new web application, ordering food items of different cuisines from a restaurant . | US001 | Admin can login in web application. | The admin can login in the portal inorder to make add,remove,edit enable disable the food items. | New
| US002 | New user can register on the website and maintain the record of activities. | Registered user can search the food items based on different cuisines. | New
| US003 | Registered User can Browse items listed | Registered User can Browse items,sorting,filtering the items based on different cuisines to get best deal. | New
| US004 | Registered User can add items to the cart | As a Registered Website User, I want to be able to add items to the cart. So that I can buy a listed product from the website. | New
| US004 | Registered User can add items to the cart | As a Registered Website User, I want to be able to add items to the cart. So that I can buy a listed food items from the website. | New
| US005 | Registered User can make payment for the items added to the cart. | Registered user can perform a seamless payment once proceed to buy a food items.
| US006 | Registered User can get summary page. | As a registered user can get summary page once the payment is done.

## Sprint Planning
Project Name | FOODBOX
Scrum Team | Dev, QA, PO, Scrum Master etc.
Created By | Product Owner
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
For a foodbox restaurant to launch a new web application, ordering food items of different cuisines from a restaurant .(FoodBox_epic_01) | US001 | Admin can login in web application. | The admin can login in the portal inorder to make add,remove,edit enable disable the food items. | 3 | 1
| US002 | New user can register on the website and maintain the record of activities. | Registered user can search the food items based on different cuisines. | 3 | 1
| US003 | Registered User can Browse items listed | Registered User can Browse items,sorting,filtering the items based on different cuisines to get best deal. | 4 | 2
| US004 | Registered User can add food items to the cart | As a Registered Website User, I want to be able to add items to the cart. So that I can buy a listed food itemst from the website. | 4 | 3
| US005 | Registered User can make payment for the food items added to the cart. | Registered user can perform a seamless payment once proceed to buy a food items. | 5 | 3
| US006 | Registered User can get summary page. | As a registered user can get summary page once the payment is done. | 3 | 4

## Testcase
TestCaseID | UserStoryID | Feature | User Story | Steps | Execpted Result
TC_DL_001 | US001 | Admin can login in web application. | The admin can login in the portal inorder to make add,remove,edit enable disable the food items. | 1) Open Application URL 2) Go to Catalog Page 3) Add the item | Admin is able to enable and disable the items.
TC_DL_002 | US002 | New user can register on the website | User can buy items cancel the order view the summary page. | 1) Open Application URL 2) Click on Registered Link 3) Update User Details 4) Click on Submit | New user should be able to register on site.

## Tasks
QA Tasks | Developer Tasks
Reviewing User Stories | Reviewing User Stories
Creating Test Cases | Setting up Development Environment
Setting up Test Environment | Developing Programs
Creating Test Data | Code Review
Executing Manual Tests | Creating Unit Test Cases
Automation Setup | Executing Unt Tests
Automation Design | Merging Code
Automating Test Cases | Creating Builds
Re-Testing Bugs | Fixing Bugs
Regression Testing
Demo User Story